## Sheet1
Task ID | Task Name | Week | Duration (Days) | Dependencies | Start Day | Task Owner
1 | Finalize Features List and System Scope | 2 | 1 | - | 9 | All
2 | Create Initial Wireframes (Home, Cart, Subscription) | 2 | 2 | 1 | 9 | Erin
3 | Define Component Architecture & Data Flow Plan | 2 | 1 | 2 | 9 | Kolton
4 | Develop Cart & Subscription UI in React | 3 | 2 | 3 | 16 | Manuel
5 | Build State Logic for Cart (Add/Remove/Update/Limit Subscriptions) | 3 | 2 | 4 | 16 | Avery
6 | Implement Local Storage for Cart Persistence | 3 | 1 | 5 | 16 | Kolton
7 | Style Components Using CSS | 3 | 1 | 4 | 16 | Erin
8 | Research Secure Credit Card Handling & PCI Compliance (Technical Focus) | 4 | 2 | 6 | 23 | Erin
9 | Build Credit Card Entry Component with Validation | 5 | 2 | 8 | 30 | Avery
10 | Integrate Checkout Button & Routing to Payment Component | 5 | 1 | 9 | 30 | Avery
11 | Implement Google OAuth Login System | 5 | 2 | 6 | 30 | Manuel
12 | Connect Auth Flow to App Routing (Gate Main App Access) | 5 | 1 | 11 | 30 | Manuel
13 | Final Bug Fixes and Refinements | 5 | 1 | 10, 12 | 30 | Avery
14 | Record final Presentation | 5 | 1 | 1-3 | 30 | All
[7 empty] | All | Erin | Kolton | Manuel | Avery